## Hoja1
Gather-Ring Expansion | Estimated Start Date | Estimated End Date | Jan 10 | Jan 15 | Jan 17 | Jan 22 | Jan 24 | Jan 29 | Jan 31 | Feb 5 | Feb 7 | Feb 12 | Feb 14 | Feb 26 | Feb 28 | Mar 5 | Mar 7 | Mar 12 | Mar 14 | Mar 19 | Mar 21 | Mar 26 | Mar 28 | Apr 2 | Apr 4 | Apr 9 | Apr 11
Overall Project | Jan 10 | Apr 11
Microcontroller Programming I | Jan 10 | Jan 17
Project Proposal and Presentation | Jan 15 | Jan 24
Microcontroller Programming II | Jan 29 | Jan 31
Design Process | Feb 5 | Feb 7
Design Reviews | Feb 12 | Feb 28
Testing and Design Iterations | Mar 5 | Mar 21
Final Designs I | Mar 26 | Mar 28
Final Designs II | Apr 2 | Apr 4
Final Designs III | Apr 11 | Apr 11
Proof of Concept | Jan 24 | Apr 11
Ordering Parts (Jan 25, Feb 1, Feb 8) | Jan 24 | Feb 7
Arduino LED Integration | Jan 29 | Jan 31
LED Controller Software | Jan 29 | Feb 14
Model Base and Structure | Feb 5 | Feb 14
Testing and Design Iterations | Feb 26 | Mar 21
Refinement | Mar 26 | Apr 11
City Proposal | Jan 24 | Apr 11